## Job
Job setup
Fill in the yellow cells. Budget lines go on the Budget tab.
Job number |  | e.g. 26-014
Job name* |  | Required
GC / client |  | Matched to your Clients & GCs list
Location
Project manager |  | Name or email of a Project Manager login
Start date
End date
Contract amount |  | Leave blank to use the total bid price
Budget structure | Bid items | Bid items or Cost codes
Default overhead % | 10% | Taken out of every line’s bid price unless the line has its own
Default markup % | 12% | Taken out of every line’s bid price unless the line has its own
Totals (calculated)
Total bid price |  | What the job was bid at
Overhead + markup |  | Taken out of the bid
Budget cost |  | What the job has to be built for
Contract used |  | Contract amount if entered, otherwise total bid price
Budgeted profit
Budgeted margin

## Budget
Item no.* | Description* | Unit | Quantity | Labor — bid | Equipment — bid | Materials — bid | Subcontract — bid | Other — bid | Bid price | Overhead % (line) | Markup % (line) | Overhead % used | Markup % used | OH + markup $ | Budget cost | Labor — budget | Equipment — budget | Materials — budget | Subcontract — budget | Other — budget | Unit bid price | Unit cost | Notes

## Instructions
Bid item budget template
What it’s for | Turning the bid into a working budget. In the app: Jobs → Import budget (new job), or open a job → Import budget lines.
Enter bid prices | On the Budget tab, enter what each bid item was BID at, split into labor, equipment, materials, subcontract and other. These are selling prices — overhead and markup are still in them.
Overhead and markup | Set the default overhead % and markup % on the Job tab. A line with different rates can have its own in the “(line)” columns. The app takes them back out: budget cost = bid price ÷ (1 + overhead %) ÷ (1 + markup %).
Budget cost | The grey columns show the result — the number the job has to be built for, split by labor, equipment, materials, subcontract and other. That is what costs are tracked against in the app.
Example | A $112,000 line with 10% overhead and 12% markup: 112,000 ÷ 1.10 ÷ 1.12 = $90,909 budget cost, $21,091 of overhead and markup.
Quantity and unit | Budget quantity drives % complete: as quantities are installed, the app projects the final cost. Lump-sum lines can be left blank and given a % complete in the app.
Contract amount | Optional on the Job tab. If blank, the contract is the total bid price.
Re-importing | Importing into an existing job only adds lines whose item no. isn’t already there. Nothing is changed or deleted.

## Example
Item no.* | Description* | Unit | Quantity | Labor — bid | Equipment — bid | Materials — bid | Subcontract — bid | Other — bid | Bid price | Overhead % (line) | Markup % (line) | Overhead % used | Markup % used | OH + markup $ | Budget cost | Labor — budget | Equipment — budget | Materials — budget | Subcontract — budget | Other — budget | Unit bid price | Unit cost | Notes
1 | Mobilization | LS | 1 | 5544 | 7392 | 0 | 0 | 1848
2 | Clearing & grubbing | AC | 14 | 12074 | 20328 | 0 | 0 | 2587
3 | Erosion control | LS | 1 | 7638 | 3819 | 14538 | 0 | 0
4 | Mass excavation | CY | 48000 | 76877 | 186278 | 0 | 0 | 0
5 | 24" RCP storm pipe | LF | 1200 | 26611 | 17741 | 72442 | 0 | 0
6 | Graded aggregate base 8" | SY | 9500 | 11704 | 14045 | 81928 | 0 | 0
7 | Asphalt paving (sub) | SY | 9500 | 0 | 0 | 0 | 156209 | 0 |  | 5% | 8%